## Лист1
PROJECT CHARTER
Name | Smart Cybersecurity Monitoring System for Small Businesses
Date | 29 October 2025
Last revised | 11 November 2025
PROJECT DEFINITION
Small companies often have limited knowledge and tools to protect themselves from cyberattacks. This project focuses on creating a simple monitoring platform that analyzes system logs and detects suspicious activity in real time. The system will send alerts to business owners, helping them react quickly and prevent damage. The solution should be easy to deploy, require minimal configuration, and work with common IT environments. The project will include requirements analysis, design, development, testing, and demonstration with sample data.
PROJECT PURPOSE
Give small businesses affordable and automated cybersecurity support. Reduce risks of data breaches and downtime. Improve awareness and response time to cyber threats.
RISKS |  | CONSTRAINTS
Scope growth due to extra features requested by stakeholders |  | Limited budget
Lack of security expertise inside the team |  | Strict timeline aligned with academic schedule
Integration issues with external log sources
Delays due to unexpected technical complexity
Technologies |  | DEPENDENCIES
Backend: Python |  | Access to test infrastructure and sample logs
Frontend: React |  | Stable internet and hosting services
Database: PostgreSQL
SUCCESS CRITERIA |  | MAJOR MILESTONES
System detects and alerts at least 80% of common suspicious events |  | Requirements and planning completed
Demo works smoothly with realistic test scenarios |  | System architecture and prototype UI
Stakeholders approve usability and reliability |  | Core functionality implemented
Testing, improvements and security audit
Final demo and project closure
KEY STAKEHOLDERS | NAME
Project Manager | Almaz Karabayev